## Slide 1: TADS
TNB(Tels) Analytics Data System Phase 1 Kick Off
August 2016
Kick Off

## Slide 2: Agenda
Project Introduction
Solution Architecture
Project Implementation Methodology
Project Organization
Responsibilities
Project Timeline
Communication Plan
Key to Success
Q&A

## Slide 3: Project Introduction
The main aim of the TADS project Phase 1 is to replace the current manual management reporting with an automated process and also do more analytics for new reporting.
The Insight gained will provide a better view of strategic information and informative decision.
The scope of project in phase 1 is Sale and Accounting
In the future, the analytics solution can be expanded to cover other areas and offer other high value functions such as Machine Learning
The project will start in August 29th 2016 and conclude by January 2017.
The TADS Phase 1 system will be developed in Business Intelligence of Group Lease PCL with the partner is Telesafe Asia.Co,.Ltd.

## Slide 4: Solution Architecture
Importing/ETL
Connectors
BD Database Server
Data Sets Container
Data Sources
Reports, Dashboards, KPIs, Graphs, GEO Maps
TNB Operational
DBMS
Data
Warehouse
Created By GL BI Team
BellaDati Application
Server

## Slide 5: Project Implementation Methodology
Requirements gathering
Prepare Functional Requirement Document (FRD)
Data Discovery and Mapping
Data Warehouse Preparation
Data Set Creation
Reports and Dashboards Development & Testing
User Acceptance Testing (UAT)
Go Live
(More details in Project Master Plan)

## Slide 6: Project Organization
Project Sponsors
Chairman
Mr.Muneo Tashiro
Mr.Freddy Marrie
Mr.Kampol Sinthaworn
Project Managers
Mr.Nattapong Laiyapark (IT)
Business Team Leader
Mr.Muneo Tashiro
IT Team Leader
Mr.Nattapong Laiyapark
Key User
Mr.Thanachart
BI Development Team
Mr.Perasan Ms.Nattida
Ms.Supawadee Mr.Chonlathep
TeleSafe Asia (Partner)
Mr.Worachai (PM)
Mr. Remi (Sr. Consultant)
Tels Development Team
Mr.Paponpat
Mr.Thanet
Server, Support and Security
Mr.Thanapol Mr. Prasopsup
Mr.Sutee

## Slide 7: Responsibilities
Chairman
  Take final decision for quotation and contracting.
  Accept the project planning, team and methodology.
  Approve changes which could have big impact on project.
Mr.Tashiro, Mr.Freddy and Mr.Kampol
  Act as emergency if people are not reactive enough during the project.
  Approve related steps validations.
Mr. Thanachart
  Provide all business requirement that project need.
  Manage the business team all over the project as required by BI team.
  Perform the testing(QA) of the reporting and so on.
  Perform the training of the reporting to all TNB users.

## Slide 8: Responsibilities
Mr. Nattapong
  Understand all business requirement and specification.
  Delegate job to BI team and transfer knowledge to TeleSafe partner.
  Manage project timeline, issues and risks.
  Perform the development and testing (QA) of the Data Warehouse.
  Perform the development and testing (QA) of the reporting
  Perform the internal training to end user as well as BI team.
Mr. Peerasan, Mr.Cholathep, Ms.Supawadee and Ms.Nattida
  Understand all business requirement and specification.
  Perform the development and testing (QA) of the Data Warehouse.
  Perform the development and testing (QA) of the reporting.
  Perform the internal training to end user as well as BI team.

## Slide 9: Responsibilities
Mr. Paponpat, Mr. Thanet
  Provide all understanding in Tels database structure.
  Should understand the business requirement for data mapping.
Mr. Prasopsub
  Act as level one for TADS support.
Mr. Thanapon, Mr. Sutee
  Provide all server for development and Production(UAT).
  Make sure the availability and speed of TADS during project and after.
  Establish data backup and DRP procedures and monitor it.

## Slide 10: Responsibilities
TeleSafe Aisa (Partner)
  Understand all business requirement and specification.
  Perform the development and testing (QA) of the reporting.
  Provide executive ideas of the reporting concept.
  Provide all training to BI developer as well as end user.

## Slide 11: Project Timeline
Requirement
Planning & Design
29/08/16
To
30/09/16
Data warehouse 03/10/16
To
28/10/16
Report Developer Training
Reporting Development
Production Deployment
31/10/16
To
28/12/16
UAT in Production
29/12/16
To
09/01/17
Go Live
12/01/17
User Training
10/01/17
To
11/01/17

## Slide 12: Communication Plan
Communication Type | Owner | Mandatory | Frequency | Agenda
Scrum Meeting | Mr.Nattapong | BI team | Daily | Update from everyone on – What was done yesterday? What is the plan for tomorrow? What are your issues?
Project Team Meeting | Mr.Nattapong | BI Team TeleSafe Asia | Weekly | Review & Discuss the project progress. Discuss upcoming milestones. Review the risk and issues log. Any other business.
Project Status & Update Report | Mr.Tashiro Mr.Freddy Mr.Kampol | BI Team Mr.Thanachart | Weekly | Status update on the key project parameters Schedule, Budget, Risks, Issues and Benefits.

## Slide 13: Key to Success
Participation - Get involved, speak up and share
Communication - Talk early and often
Teamwork - Work together to keep projects coordinated
Have fun!

## Slide 14: Q & A
Q & A